## Description
Text Transformer
For people working with text data, our Text Transformer application will allow you to transform text data (e.g. change case, eliminate duplicates, etc.). The application will be available via GUI as well as remote API, thanks to which it will be possible to integrate it with existing tools.

## Product Backlog
Product Backlog item | Importance | Labour intensity | Business Value (BV) | Acceptance Criteria
As an application developer, I can invoke a transformation remotely via REST to be able to integrate the tool with my other apps | 15 | 8 | 1 | o Input in the form of text and transformation sequence (names) o Input and output in JSON format o REST API allows to run any currently implemented transformation or transformation sequence
As a user, I can modify the case of letters - a set of three transformations (upper, lower, capitalize) | 12 | 4 | 0.5 | o Change case of letters - set of three transformations (upper, lower, capitalize) • upper - all letters to uppercase: upper -> UPPER • lower – all letters to lowercase: Lower -> lower • capitalize – the first letter in each word to uppercase: capitalize text -> Capitalize Text • Support for letters from the English alphabet (UTF-8)
As a user, I can reverse the sequence of characters, retaining the case of letters in specific positions (inverse) | 10 | 3 | 0.5 | • Preserving the positions of upper and lower case letters: MirEk -> KerIm • Reverse sequence of characters • Support for all UTF-8 characters
As a user, I can convert numbers into text in English (donate 100 dollars -> donate one hundred dollars) - support for the range of numbers to be negotiated | 10 | 5 | 1 | • conversion of integers to 1000 • conversion of floating point numbers to hundredths
As a user, I can replace selected (predefined) words with acronyms (Bread is, for example rolls -> Bread is, e.g. rolls) - the range of supported shortcuts to negotiate | 10 | 3 | 0.5 | • Acronym expansion: for example -> e.g. • Acronym expansion: among others -> i.a. • Acronym expansion: and so on -> aso • Works regardless of case
As a user, I can expand selected acronyms to full strings (Professor was late for classes -> Prof. was late for classes) | 10 | 3 | 0.5 | • prof. -> professor • dr -> doctor • e.g. -> for example • aso -> and so on • Preserves case: E.g. -> For example
As a user I can convert text to Latex supported format (special characters) -> (John Smith & Sons -> John Smith \& Sons) | 2 | 2 | 0.5 | • & -> \& • $ -> \$
As a user, I can eliminate repetitive words in the immediate vicinity (Send me me a message -> Send me a message) | 1 | 4 | 1 | • Convert two repeated words to one: to to -> to • Convert any number of words repeated: to to to -> to • Replace all repetitions within a text: to to after after -> to after • Works well with all UTF-8 characters
As a user, I can utilise the application via the user interface |  |  |  | To be negotiated later

## Sprint #1 Backlog
Sprint Goal: | Build the first working version of Text Transformer with a REST API and core text transformation features.
Product Backlog Item | Tasks | Labour intensity
As a developer, I can invoke text transformations via REST API. |  | 8
| Task #1 Learning about REST API structure in the starter project | 1
| Task #2 Creating/adjusting REST endpoint for text transformation | 2
| Task #3 Reading input text and transformation sequence from request | 1
| Task #4 Returning input and output in JSON format | 1
| Task #5 Connecting endpoint with transformation logic | 1
| Task #6 Validating and testing REST requests | 1
| Task #7 Debugging and cleaning code | 1
As a user, I can modify the case of letters - a set of three transformations (upper, lower, capitalize) |  | 4
| Task #1 Implementing upper transformation | 1
| Task #2 Implementing lower transformation | 1
| Task #3 Implementing capitalize transformation | 1
| Task #4 Testing and correcting case transformations | 1
As a user, I can reverse the sequence of characters, retaining the case of letters in specific positions |  | 3
| Task #1 Implementing reverse character sequence | 1
| Task #2 Preserving upper/lower case positions | 1
| Task #3 Testing and correcting inverse transformation | 1
As a user, I can convert numbers into text in English |  | 5
| Task #1 Implementing integer conversion from 1 to 1000 | 2.5
| Task #2 Implementing decimal/hundredths conversion | 1
| Task #3 Testing number conversion examples | 1
| Task #4 Debugging and cleaning code | 0.5
As a user, I can replace selected predefined words with acronyms |  | 3
| Task #1 Implementing word-to-acronym replacement | 1
| Task #2 Making replacement case-insensitive | 1
| Task #3 Testing and correcting acronym replacement | 1
As a user, I can expand selected acronyms to full strings |  | 3
| Task #1 Replacing full phrases with acronyms in text | 1
| Task #2 Making replacement work regardless of case | 1
| Task #3 Testing examples | 0.5
| Task #4 Debugging and cleaning code | 0.5
As a user I can convert text to Latex supported format |  | 2
| Task #1 Implementing escaping for $ and & characters | 1
| Task #2 Testing LaTeX escaping examples | 0.5
| Task #3 Debugging and correcting LaTeX transformation | 0.5
As a user, I can eliminate repetitive words in the immediate vicinity |  | 4
| Task #1 Implementing removal of two repeated words | 1
| Task #2 Implementing removal of multiple repeated words | 1
| Task #3 Testing repeated words in longer text | 1
| Task #4 Debugging and cleaning code | 1
Sprint 1 Setup |  | 3.5
| Task #1 Setting up GitHub repository | 1
| Task #2 Uploading starter project architecture | 0.5
| Task #3 Configuring GitHub Actions build | 1
| Task #4 Creating GitHub Issues and Sprint 1 milestone | 1
Sprint 1 Documentation |  | 3
| Task #1 Preparing UML class diagram | 1.5
| Task #2 Preparing sequence diagram | 1.5

## Sprint #2 Backlog
Sprint Goal: | Ensure the quality of the increment through automated unit tests and complete documentation, and deliver a properly tagged v0.2 release.
Product Backlog Item | Tasks | Labour intensity
Unit testing of the transformation logic and REST controller |  | 8
| Task #1 Unit tests for CaseModifier, TextReverser and the controller | 2
| Task #2 Unit tests for NumberToTextConverter, AcronymExpander, AcronymReplacer | 2
| Task #3 Unit tests for LatexConverter, RepetetiveWordEliminator, TextTransformer | 2
| Task #4 Mock-object tests verifying decorator delegation | 1
| Task #5 Run the full test suite and fix failures | 1
Complete code documentation (Javadoc) |  | 4
| Task #1 Add Javadoc to all logic classes (class, methods, fields) | 2
| Task #2 Add Javadoc to model and REST classes | 1
| Task #3 Verify Javadoc builds without errors (mvn javadoc:jar) | 1
Release v0.2 of the increment |  | 3
| Task #1 Bump version to 0.2 in pom.xml | 0.5
| Task #2 Build package and confirm the Javadoc jar is produced | 1
| Task #3 Tag v0.2 and publish GitHub release with app + Javadoc jars | 1.5
Sprint 1 retrospective and improvements |  | 3
| Task #1 Document retrospective improvements on the project wiki | 1
| Task #2 Improvement: maintain a Definition-of-Done checklist verified before each release | 0.5
| Task #3 Improvement: assign an owner to each non-code deliverable (diagrams, docs) | 0.5
| Task #4 Improvement: agree a shared documentation standard | 0.5
| Task #5 Improvement: better time management - earlier deadlines and continuous integration | 0.5
New Product Backlog items for future sprints |  | 1
| Task #1 Propose 4-6 new user stories with acceptance criteria | 1